{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Map","Schedule","Graphic Overview","Help","Data","Map_Backup"],"not_rendered":{"charts":0,"images":4,"macros":1,"external_links":0,"defined_names":2,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":101,"n_cols":1,"rows_kept":101,"cut":false,"hidden":false,"merged":[[100,0,100,3]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Last update: 12 January 2021"]

{"sheet":"Schedule","index":1,"n_rows":60,"n_cols":34,"rows_kept":60,"cut":false,"hidden":false,"merged":[[1,31,2,31],[1,32,2,32],[1,33,2,33],[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination",null,"IM\nProject ID\n(Optional)","Last update","cancelled"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Rerouting","Train replacement","Delays","Other",null,null,"In yearly timetable"]
[null,"PKP PLK-SA","51_11_2401","Tunel - Radom","<","Sędziszew","Kozłów",2025,2026,32,32,"2025-08-10","00:00:00","2026-08-09",1,"269 days","continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"modernization, 4 hours total closure during night",null,"Y",null,"2024-12-05","N"]
[null,"PKP PLK-SA","51_11_2406","Muszyna - Kraków","< >"," Tarnów Filia","Leluchów GP",2026,2026,9,27,"2026-03-01","00:00:00","2026-06-30",1,"122 days","continuous","Track & Rail","T","LT",null,null,null,null,"R",null,null,null,"one track line, total closure",null,"N",null,"2024-12-05","N"]
[null,"PKP PLK-SA","51_11_2503","Muszyna - Kraków","< >","Nowy Sącz","Muszyna",2027,2027,35,44,"2027-09-01","00:00:00","2027-11-05",1,"66 days","continuous","Track & Rail","T","LT",null,null,null,null,"R",null,null,null,"one track line, total closure",null,"N",null,"2024-12-05"]
[null,"PKP PLK-SA","51_11_2501","Tunel - Radom","<","Kielce Białogon","Sitkówka Nowiny",2026,2026,30,37,"2026-07-20","00:00:00","2026-09-11",1,"55 days","continuous","Bridge",null,"LT","S",null,null,null,null,null,null,null,"single track operations, major TCR",null,"N",null,"2024-12-05"]
[null,"PKP PLK-SA","51_11_2502","Tunel - Radom","<","Sitkówka Nowiny","Radkowice",2025,2026,24,2,"2025-06-12","00:00:00","2027-01-09",1,"364 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"single track operations, major TCR",null,"Y",null,"2024-12-05"]
[null,"ŽSR","56KE2212132","Hidasnémeti - Košice ","< >","Nižná Myšľa","Ruskov",2024,2026,35,18,"2024-09-01","08:00:00","2026-04-30",0.66666666666666663," days","periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101",null,null,null,"2023-06-23"]
[null,"ŽSR","56TT2311011a","Nové Zámky - Leopoldov","< >","Križovany n/Dudváhom","Trnava",2025,2026,1,9,"2025-01-01","08:00:00","2026-02-28",0.70833333333333337,"423 days","periodical","Signal",null,null,null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia ",null,null,null,"2024-08-02"]
[null,"ŽSR","056KE2212136","Medzilaborce - Trebišov - Slivník","< >","Bánovce nad Ondavou","Humenné",2024,2025,1,40,"2024-01-01T08:00:00",45292.333333333336,"2025-09-30T16:00:00",0,null,"periodical","Others","T","LT+ST",null,null,null,null,"R",null,null,"O","10","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056KE2212131","Čop - SNM (Sátoraljaújhely) - SNM - Štrba","< >","Veľký Horeš","Streda nad Bodrogom",2024,2025,14,14,"2024-04-01T08:00:00",45383.333333333336,"2025-12-31",0,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056KE2306001","Plaveč - Kysak","< >","Prešov","Strážske",2024,2028,27,5,"2024-07-01T08:00:00",45474.333333333336,"2028-01-31T16:00:00",0,null,"periodical","Signal",null,null,null,null,null,null,null,null,null,null,"107","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056KE2212134","Čop - SNM (Sátoraljaújhely) - SNM - Štrba","< >","Spišská Nová Ves","Vydrník",2024,2026,31,31,"2024-08-01T08:00:00",45505.333333333336,"2026-07-31T16:00:00",0,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"105","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056KE2212132","Čop - SNM (Sátoraljaújhely) - SNM - Štrba","< >","Nižná Myšľa","Ruskov",2024,2026,35,18,"2024-09-01T08:00:00",45536.333333333336,"2026-04-30T16:00:00",0,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056KE2212131","Čop - SNM (Sátoraljaújhely) - SNM - Štrba","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01T08:00:00",45778.333333333336,"2026-06-30T16:00:00",0,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101","","Y",null,"2024-12-12","N"]
[null,"ŽSR",null,"Čop - SNM (Sátoraljaújhely) - SNM - Štrba","< >","Košice","Košice",2025,2025,28,52,"2025-06-01","08:00:00","2025-12-31",0.66666666666666663,null,"periodical","Signal",null,null,null,null,null,null,null,null,null,null,"modernizácia stavadla",null,"Y",null,"2024-12-12","N"]
[null,"ŽSR","A14256","Čop - SNM (Sátoraljaújhely) - SNM - Štrba","< >","Košice","Košice",2025,2025,28,52,"2025-06-01","08:00:00","2025-12-31",0.66666666666666663,null,"periodical","Others",null,null,null,null,null,null,null,null,null,null,"rekonštrukcia nástupišť",null,"Y","A14256","2024-12-12","N"]
[null,"ŽSR","TC/0056/VY0000003342/00/2025","PKP Plaveč - Kysak","< >","Prešov","Veľký Šariš",2025,2025,20,36,"2025-06-02","08:00:00","2025-10-31",0.70833333333333337,"151days","continuous","Track & Rail","T","LT+ST",null,null,null,null,"R",null,"D","O","Comprehensive track reconstruction",null,"Y","A17093","2024-12-12","N"]
[null,"ŽSR","A13225","Medzilaborce - Trebišov - Slivník","< >","Bánovce nad Ondavou","Humenné",2025,2026,1,52,"2025-11-01","00:01:00","2026-06-01",0.66666666666666663,null,"periodical continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Comprehensive modernisation , track+swith+platforms",null,"Y","A13225","2024-12-12","N"]
[null,"ŽSR","A14198","Medzilaborce - Trebišov - Slivník","< >","Výhybňa Slivník","Výhybňa Slivník",2026,2027,20,8,"2026-06-01","08:00:00","2027-02-28",0.66666666666666663,null,"periodical","Track & Rail",null,null,null,null,null,null,null,null,null,null,"switch modernisation num.1 - 10",null,"Y","A14198","2024-12-12","N"]
[null,"ŽSR","56TT2311011b","Bratislava hl.st. - Trnava - Nové Mesto nad Váhom","< >","Bratislava-Rača","Trnava",2025,2026,1,9,"2025-01-01T08:00:00",45658.333333333336,"2026-02-28T17:00:00",0,"371 x 23h 59min every week","periodical","Signal",null,null,null,null,null,null,null,null,null,null,"CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056TT2311014","Bratislava hl.st. - Dunajská Streda - Komárno","< >","Bratislava-Nové Mesto","Nové Košariská",2026,2026,1,53,"2026-01-01T08:00:00",46023.333333333336,"2026-12-31T17:00:00",0,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Vybudovanie odb. Ružinov, rozšírenie stanice N. Košariská, AH N. Košariská - Kvetoslavov","","Y",null,"2024-12-12","N"]
[null,"ŽSR","56TT2311011a","Trnava - Sereď - Galanta","< >","Trnava","Križovany nad Dudváhom",2026,2026,1,9,"2026-01-01T08:00:00",46023.333333333336,"2026-02-28T17:00:00",0,"371 x 23h 59min every week","periodical","Signal",null,null,null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia Trnava - Križovany","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056TT2311013","Bratislava hl.st. - Bratislava-Petržalka št.hr.","< >","Bratislava ÚNS","Bratislava-Petržalka",2026,2026,1,53,"2026-01-01T08:00:00",46023.333333333336,"2026-12-31T17:00:00",0,null,"periodical","Track & Rail",null,null,null,null,null,null,null,null,null,null,"Rekonštrukcia koľají č. 1, 2 (mimo DŽM)","","Y",null,"2024-12-12","N"]
[null,"ŽSR","056TT2311009","Bratislava hl.st. - Bratislava-Petržalka št.hr.","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2026,2026,1,53,"2026-01-01T08:00:00",46023.333333333336,"2026-12-31T17:00:00",0,null,"periodical","Track & Rail",null,null,null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2","","Y",null,"2024-12-12","N"]
[null,"ŽSR","A12084","Vrútky - Žilina-Teplička - Žilina","< >","Žilina zr.stanica","Žilina",2023,2026,1,53,"01.01.2025","00:01","31.03.2026",0,null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Modernizácia celého železničného uzla",null,"Y","A12084","2024-12-12","N"]
[null,"ŽSR","A10044.1","Žilina - Čadca - Mosty u Jablunkova (ČD)","< >","Čadca","Krásno nad Kysucou",2025,2025,36,44,"1.9.2025","08:00","30.10.2025",0.70833333333333337,null,"periodical","Track & Rail",null,null,null,null,null,null,null,null,null,null,"Modernizácia trate - Stabilizácia zosuvu trate",null,"Y","A10044.1","2024-12-12","N"]
[null,"ŽSR","A11108","Bratislava hl.st. - Dunajská Streda - Komárno","< >","Bratislava Nové Mesto","Dunajská Streda","2025","2025","1","52","01.01.2025","08:00","31.12.2025",0,"365","continuous","Bridge",null,null,null,null,null,null,null,null,null,null,"Komplexná rekonštrukcia mostného objektu v km 7.892",null,"Y","A11108","2024-12-12","N"]
[null,"ŽSR","TC/0056/VY0000003467/00/2025","Bratislava hl.st. - Petržalka št.hr - Rusovce št.he","< >","Bratislava ústredná nákladná stanica","Bratislava-Nové Mesto",2025,2025,9,50,"2025-03-02","08:00:00","2025-12-13",0.70833333333333337,"286days","periodical","Miscellaneous",null,"LT","S",null,null,null,null,null,"D","O","Modernisation",null,"Y",null,"2024-12-12","N"]
[null,"ŽSR","TC/0056/VY0000003412/00/2025","Púchov - Lúky pod Makytou","< >","Púchov","Lúky pod Makytou št.hr.",2025,2025,44,48,"2025-11-01","08:00:00","2025-11-30",0.70833333333333337,"29days","continuous","Track & Rail","T","LT+ST",null,null,null,null,"R",null,null,"O","Comprehensive recontruction of the track",null,null,null,"2024-12-12"]
[null,"MAV",5511150002,"Kelebia - Kiskunhalas","< >","Kiskunhalas","Kelebia",2023,2024,50,50,"2023-12-10","00:00:00","2024-12-14",0.99930555555555556,"370 days + 23 h 59 min","continuous","Track & Rail","T",null,null,null,null,null,"R",null,"D",null,"Total closure",null,null,null,"2022-08-23"]
[null,"GySEV/Raaberbahn",null,"Csorna - Rajka","< >","Csorna","Hegyeshalom",2025,2025,15,15,"2025-04-07",null,"2025-04-11",null,"4 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Change of switches in Bősárkány",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Győr - Csorna","< >","Győr","Csorna",2025,2025,17,18,"2025-04-22",null,"2025-04-29",null,"5 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and level crossing",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Csorna - Fertőszentmiklós","< >","Csorna","Fertőszentmiklós",2025,2025,20,21,"2025-05-12",null,"2025-05-22",null,"10 days","continuous","Catenary","T",null,null,null,null,null,"R",null,null,null,"Ballast tamping, track, catenary and switch reconstruction",null,null,null,"2024-04-03"]
[null,"GySEV/Raaberbahn",null,"Bősárkány - Mosonszolnok","< >","Bősárkány","Mosonszolnok",2025,2025,22,23,"2025-05-25",null,"2025-06-06",null,"12 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Ballast tamping, track, catenary and switch reconstruction",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Szombathely - Sopron","< >","Lővő","Sopron",2025,2025,26,26,"2025-06-23",null,"2025-06-26",null,"3 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Substructure and catenary maintenance",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Répcelak - Csorna","< >","Porpác","Csorna",2025,2025,27,29,"2025-07-01",null,"2025-07-15",null,"14 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track, catenary and switch reconstruction",null,null,null,"2024-04-03"]
[null,"GySEV/Raaberbahn",null,"Szombathely - Sopron","< >","Bük","Harka",2025,2025,31,31,"2025-07-28",null,"2025-07-31",null,"3 days","continuous","Catenary","T",null,null,null,null,null,"R",null,null,null,"Catenary maintenance",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Szombathely-Rendező - Zalaszentiván","< >","Szombathely-Rendező","Zalaszentiván",2025,2025,32,33,"2025-08-04",null,"2025-09-22",null,"13 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and level crossing and bridge reconstruction",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Fertőszentmilklós - Sopron","< >","Fertőszentmiklós","Sopron",2025,2025,37,40,"2025-09-01",null,"2025-09-30",null,"22 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track, catenary and bridge reconstruction",null,null,null,"2024-12-06"]
[null,"GySEV/Raaberbahn",null,"Hegyeshalom - Rajka","< >","Hegyeshalom","Rajka",2025,2025,42,46,"2025-10-13",null,"2025-11-10",null,"29 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and bridge reconstruction",null,null,null,"2024-04-03"]
[null,"SŽ",791004,"Ljubljana - Celje","< >","Sava","Litija",2025,2025,21,22,"2025-05-20","09:00:00","2025-05-28",0.875,"8 days + 12 h 0 min","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-06-27"]
[null,"SŽ",795008,"Koper - Ljubljana","< >","Postojna","Prestranek",2025,2025,38,39,"2025-06-19","07:00:00","2025-06-24",0.91666666666666696,"5 days + 13 h 0 min","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-06-27"]
[null,"SŽ",795008,"Koper - Ljubljana","< >","Verd","Logatec",2025,2025,18,18,"2025-06-12","07:00:00","2025-06-17",0.91666666666666696,"5 days + 15 h 0 min","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-06-27"]
[null,"SŽ",795007,"Koper - Ljubljana","< >","Pivka","Gornje Ležeče",2025,2025,27,31,"2025-07-05","08:00:00","2025-08-10",0.83333333333333304,"36 days + 12 h 0 min","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-06-27"]
[null,"SŽ",7901,"Koper - Ljubljana","< >","Koper","Divača",2025,2025,14,14,"2025-03-30","07:00:00","2025-03-31",0.66666666666666663,"1 days + 9 h 59 min","continuous","Maintenance",null,"LT+ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-06-27"]
[null,"SŽ",7902,"Koper - Ljubljana","< >","Koper","Divača",2025,2025,21,21,"2025-05-25","07:00:00","2025-05-26",0.79166666666666663,"1 days + 12 h 0 min","continuous","Maintenance",null,"LT+ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-06-27"]
[null,"SŽ",7903,"Koper - Ljubljana","< >","Koper","Divača",2025,2025,41,42,"2025-10-12","08:00:00","2025-10-13",0.70833333333333304,"1 days + 9 h 59 min","continuous","Maintenance",null,"LT+ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-26"]
[null,"SŽ",7904,"Koper - Ljubljana","< >","Koper","Divača",2025,2025,45,46,"2025-11-09","09:00:00","2025-11-10",0.75,"1 days + 9 h 59 min","continuous","Maintenance",null,"LT+ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-27"]
[null,"SŽ",7905,"Koper - Ljubljana","< >","Ljubljana","Brezovica",2025,2025,11,11,"2025-03-10","07:00:00","2025-03-14",0.70833333333333337,"4 days 10h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7910,"Ljubljana - Celje","< >","Litija","Litija",2025,2025,1,4,"2025-01-01","07:00:00","2025-01-26",0.79166666666666663,"25 days 12h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Ljubljana - Celje","< >","Laze","Ljubljana Zalog",2025,2025,24,29,"2025-06-15","07:00:00","2025-07-14",0.79166666666666663,"29 days + 12 h 0 min","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Ljubljana - Celje","< >","Litija","Kresnice",2026,2026,18,22,"2026-05-01","10:00:00","2026-05-30",0.79166666666666696,"29 days + 9 h 59 min","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Ljubljana - Celje","< >","Zagorje","Sava",2026,2026,23,27,"2026-06-01","11:00:00","2026-06-30",0.83333333333333304,"29 days + 9 h 0 min","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Koper - Ljubljana","< >","Borovnica","Verd",2026,2026,9,19,"2026-03-01","12:00:00","2026-05-05",0.875,"65 days + 9 h 0 min","continuous","Track & Rail",null,"ST",null,null,null,"C",null,"B",null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Koper - Ljubljana","< >","Borovnica","Verd",2026,2026,19,28,"2026-05-06","13:00:00","2026-07-10",0.91666666666666696,"65 days + 9 h 0 min","continuous","Track & Rail",null,"LT",null,null,null,"C",null,"B",null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Koper - Ljubljana","< >","Borovnica","Verd",2026,2026,28,40,"2026-07-11","14:00:00","2026-09-30",0.95833333333333304,"81 days + 9 h 0 min","continuous","Track & Rail",null,"LT",null,null,null,"C",null,"B",null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7906,"Koper - Ljubljana","< >","Borovnica","Verd",2026,2026,40,51,"2026-10-01","15:00:00","2026-12-15",1,"75 days + 9 h 0 min","continuous","Track & Rail",null,"ST",null,null,null,"C",null,"B",null,null,"maintenance",null,"N",null,"2024-11-28"]
[null,"SŽ",7907,"Koper - Ljubljana","< >","Ljubljana","Brezovica",2025,2025,16,16,"2025-04-18","00:00:00","2025-04-21",0.16666666666666666,"3 days 4h","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2024-11-28"]

{"sheet":"Graphic Overview","index":2,"n_rows":79,"n_cols":375,"rows_kept":79,"cut":false,"hidden":false,"merged":[[3,371,3,373],[2,252,2,281],[2,282,2,312],[2,313,2,342],[2,343,2,373],[3,350,3,356],[3,357,3,363],[3,364,3,370],[3,9,3,13],[3,14,3,20],[3,21,3,27],[3,28,3,34],[3,35,3,41],[3,91,3,97],[3,98,3,104],[3,105,3,111],[3,42,3,48],[3,49,3,55],[3,56,3,62],[3,63,3,69],[3,70,3,76],[2,221,2,251],[3,329,3,335],[3,336,3,342],[3,343,3,349],[3,287,3,293],[3,294,3,300],[3,301,3,307],[3,308,3,314],[3,315,3,321],[3,322,3,328],[3,252,3,258],[3,259,3,265],[3,266,3,272],[3,273,3,279],[3,280,3,286],[3,217,3,223],[3,224,3,230],[3,231,3,237],[3,238,3,244],[3,245,3,251],[3,203,3,209],[3,210,3,216],[3,147,3,153],[3,154,3,160],[3,161,3,167],[3,168,3,174],[3,175,3,181],[3,182,3,188],[3,189,3,195],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[3,196,3,202],[2,190,2,220],[3,77,3,83],[3,84,3,90],[2,99,2,128],[2,129,2,159],[2,160,2,189],[3,112,3,118],[3,119,3,125],[3,126,3,132],[3,133,3,139],[3,140,3,146]]}
[null,"Baltic-Adriatic, Overview"]
[]
[null,null,null,null,null,null,2025,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,1,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Sędziszew - Kozłów",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Tunel - Radom","continuous","2025-08-10","2026-08-09","269 days","PKP PLK-SA"]
[]
[null,"Sitkówka Nowiny - Radkowice",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Tunel - Radom","continuous","2025-06-12","2027-01-09","364 days","PKP PLK-SA"]
[]
[null,"Nižná Myšľa - Ruskov",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Hidasnémeti - Košice ","periodical","2024-09-01","2026-04-30"," days","ŽSR"]
[]
[null,"Križovany n/Dudváhom - Trnava",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Nové Zámky - Leopoldov","periodical","2025-01-01","2026-02-28","423 days","ŽSR"]
[]
[null,"Győr - Csorna",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Győr - Csorna","continuous","2025-04-24","2025-04-29","5 days","GySEV/Raaberbahn"]
[]
[null,"Csorna - Fertőszentmiklós",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Csorna - Fertőszentmiklós","continuous","2025-05-12","2025-05-22","10 days","GySEV/Raaberbahn"]
[]
[null,"Bősárkány - Mosonszolnok",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Bősárkány - Mosonszolnok","continuous","2025-05-26","2025-06-06","12 days","GySEV/Raaberbahn"]
[]
[null,"Lövő - Bük",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Lövő - Bük","continuous","2025-06-16","2025-06-21","5 days","GySEV/Raaberbahn"]
[]
[null,"Répcelak - Csorna",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Répcelak - Csorna","continuous","2025-07-01","2025-07-15","14 days","GySEV/Raaberbahn"]
[]
[null,"Szombathely-Rendező - Zalaszentiván",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Szombathely-Rendező - Zalaszentiván","continuous","2025-08-04","2025-08-17","13 days","GySEV/Raaberbahn"]
[]
[null,"Fertőszentmiklós - Sopron",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Fertőszentmilklós - Sopron","continuous","2025-09-08","2025-09-30","22 days","GySEV/Raaberbahn"]
[]
[null,"Hegyeshalom - Rajka",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Hegyeshalom - Rajka","continuous","2025-10-13","2025-11-10","29 days","GySEV/Raaberbahn"]
[]
[null,"Laze - Ljubljana Zalog",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Ljubljana - Celje","continuous","2025-07-05","2025-08-17","43 days + 12 h 0 min","SŽ"]
[]
[null,"Brezovica - Borovnica",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-01-01","2025-04-06","95 days + 12 h 59 min","SŽ"]
[]
[null,"Brezovica - Brezovica",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-01-01","2025-04-06","95 days + 12 h 59 min","SŽ"]
[]
[null,"Preserje - Preserje",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-01-02","2025-04-06","94 days + 12 h 0 min","SŽ"]
[]
[null,"Rakek - Postojna",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-08-15","2025-08-20","5 days + 13 h 59 min","SŽ"]
[]
[null,"Rakek - Postojna",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-08-22","2025-08-25","3 days + 14 h 59 min","SŽ"]
[]
[null,"Postojna - Prestranek",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-09-16","2025-09-22","6 days + 15 h 0 min","SŽ"]
[]
[null,"Verd - Logatec",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-04-30","2025-05-05","5 days + 15 h 0 min","SŽ"]
[]
[null,"Pivka - Gornje Ležeče",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-07-01","2025-07-29","28 days + 12 h 0 min","SŽ"]
[]
[null,"Ljubljana - Ljubljana",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Koper - Ljubljana","continuous","2023-12-10","2026-12-31","721 days + 12 h 59 min","SŽ"]
[]
[null,"Koper - Divača",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-08-15","2025-08-17","2 days + 9 h 59 min","SŽ"]
[]
[null,"Koper - Divača",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Koper - Ljubljana","continuous","2025-09-21","2025-09-22","1 days + 9 h 59 min","SŽ"]
[]
[null,"Ljubljana - Ljubljana",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Koper - Ljubljana","continuous","2023-12-10","2025-11-30","721 days + 12 h 59 min","SŽ"]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":39,"n_cols":20,"rows_kept":39,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction","Direction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other","In yearly timetable","cancelled"]
["PKP PLK-SA",51,"Koper - Ljubljana",1,"continuous",11729,"Signal","< >","T","LT","S","W","D","C","R","B","D","O","Y","Y"]
["ŽSR",56,"Ljubljana - Celje",2,"periodical",null,"Switch",">",null,"ST",null,"L",null,null,null,null,null,null,"N","N"]
["MAV",55,"Celje - Hodoš",3,"periodical continuous",null,"Catenary","<",null,"LT+ST",null,"P"]
["GySEV/Raaberbahn",43,"Hodoš - Zalaszentiván",4,null,null,"Track & Rail",null,null,null,null,"W+L"]
["SŽ",79,"Zalaszentiván - Szombathely",5,null,null,"Tunnel",null,null,null,null,"W+P"]
[null,null,"Szombathely - Sopron",6,null,null,"Bridge",null,null,null,null,"L+P"]
[null,null,"Szombathely - Csorna",7,null,null,"Miscellaneous",null,null,null,null,"W+L+P"]
[null,null,"Sopron - Csorna",8,null,null,"Maintenance"]
[null,null,"Csorna - Komárom",9,null,null,"Others"]
[null,null,"Kelebia - Kiskunhalas",10]
[null,null,"Kiskunhalas - Budapest",11]
[null,null,"Budapest - Hatvan",12]
[null,null,"Kiskunhalas - Szolnok",13]
[null,null,"Szolnok - Hatvan",14]
[null,null,"Budapest - Komárom",15]
[null,null,"Komárom - Nové Zámky",16]
[null,null,"Csorna - Rajka",17]
[null,null,"Budapest -  Nové Zámky",18]
[null,null,"Hatvan - Miskolc",19]
[null,null,"Miskolc - Hidasnémeti",20]
[null,null,"Hidasnémeti - Košice ",21]
[null,null,"Rajka - Bratislava",22]
[null,null,"Bratislava - Leopoldov",23]
[null,null,"Nové Zámky - Leopoldov",24]
[null,null,"Leopoldov -  Žilina",25]
[null,null,"Žilina - Skalité",26]
[null,null,"Košice - Muszyna",27]
[null,null,"Muszyna - Kraków",28]
[null,null,"Skalité - Oświęcim",29]
[null,null,"Oświęcim - Kraków",30]
[null,null,"Oświęcim - Katowice",31]
[null,null,"Katowice - Tunel",32]
[null,null,"Kraków - Tunel",33]
[null,null,"Tunel - Radom",34]
[null,null,"Radom - Dęblin",35]
[null,null,"Dęblin - Małaszewicze",36]
[null,null,"Dęblin - Warszawa",37]
[null,null,"Radom - Warszawa",38]

{"sheet":"Map_Backup","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}